## Test Cases
LinkedIn Agent — Full Project Test Cases
Test ID | Feature Area | Test Case Title | Test Steps | Expected Result | Actual Result | Status | Tester | Comments | Priority
LOGIN-001 | Login & Account | Register a new account | 1. Open /register 2. Enter email, username, password (8+ chars) 3. Submit | Account is created, 'Account created!' toast shows and user lands inside the app |  | Pass |  |  | Important
LOGIN-002 | Login & Account | Register with invalid / existing data | 1. Open /register 2. Try an already-used email, a short password, an empty field | Clear error message for each case; no account created |  | Pass |  |  | Medium
LOGIN-003 | Login & Account | Login with valid credentials | 1. Open /login 2. Enter correct email + password 3. Submit | 'Welcome back!' toast, user lands on the app with their workspace loaded |  | Not Started |  |  | Important
LOGIN-004 | Login & Account | Login with wrong password | 1. Open /login 2. Enter wrong password | Error toast from backend; user stays on login page |  | Not Started |  |  | Important
LOGIN-005 | Login & Account | Protected pages need login | 1. Log out 2. Open /linkedin/automation directly in the URL bar | User is sent to /login; no app page is shown |  | Not Started |  |  | Important
LOGIN-006 | Login & Account | Sign out | 1. Click profile in sidebar 2. Click Sign out 3. Confirm | Confirm dialog shows first; after confirm user is logged out and sent to /login |  | Not Started |  |  | Medium
LOGIN-007 | Login & Account | Expired / invalid session | 1. Log in 2. Make the token invalid (log out from another tab or wait for expiry) 3. Do any action | User is logged out and redirected to /login (no broken page) |  | Not Started |  |  | Medium
LOGIN-008 | Login & Account | Settings page shows user details | 1. Open Settings from the sidebar | User's details are shown correctly (read-only) |  | Not Started |  |  | Low
WS-001 | Workspace | Switch workspace | 1. Open workspace switcher in sidebar 2. Pick another workspace | All data (posts, knowledge, settings, chats) changes to the selected workspace |  | Not Started |  |  | Important
WS-002 | Workspace | Workspace survives reload | 1. Pick a workspace 2. Reload the page | Same workspace is still active; ?workspace= stays in the URL |  | Not Started |  |  | Medium
WS-003 | Workspace | Data isolation between workspaces | 1. Add a knowledge source / generate a post in Workspace A 2. Switch to Workspace B | Nothing from Workspace A is visible in Workspace B |  | Not Started |  |  | Important
WS-004 | Workspace | Switch workspace on Edit Image page | 1. Open /linkedin/edit-image/<post> 2. Switch to another workspace | 'Post not found in this workspace' screen with 'Go to Agent' and 'Post Management' buttons |  | Not Started |  |  | Low
NAV-001 | Navigation & Layout | Sidebar links open the right pages | 1. Click Automation, Accounts & Knowledge, Post Management, Settings | Each opens the correct page; active item is highlighted |  | Not Started |  |  | Medium
NAV-002 | Navigation & Layout | Collapse / expand sidebar | 1. Click collapse button 2. Hover icons 3. Expand again | Sidebar collapses to icons with tooltips and expands back |  | Not Started |  |  | Low
NAV-003 | Navigation & Layout | Coming-soon items | 1. Look at Leads Management in the sidebar | Shows 'Soon' badge and can't be opened |  | Not Started |  |  | Low
NAV-004 | Navigation & Layout | Small screen layout | 1. Open main pages at tablet / mobile width | Pages are usable; no broken overlaps or cut-off buttons |  | Not Started |  |  | Low
ACC-001 | LinkedIn Account Connection | Connect LinkedIn account | 1. Open Accounts & Knowledge 2. Click Connect 3. Approve on LinkedIn | Returns to the app, 'LinkedIn account connected!' toast, account shown as connected |  | Not Started |  |  | Important
ACC-002 | LinkedIn Account Connection | Cancel / fail LinkedIn connection | 1. Click Connect 2. Cancel on the LinkedIn page | 'Failed to connect LinkedIn account.' toast; nothing marked connected |  | Not Started |  |  | Medium
ACC-003 | LinkedIn Account Connection | Disconnect LinkedIn account | 1. Click Disconnect on a connected account | 'LinkedIn account disconnected.' toast, account removed |  | Not Started |  |  | Medium
ACC-004 | LinkedIn Account Connection | Account is used for publishing | 1. Connect account 2. Schedule a post (see PUB cases) | Post is published to the connected LinkedIn account |  | Not Started |  |  | Important
KB-001 | Knowledge Base | Add LinkedIn profile | 1. Open Knowledge base modal 2. Enter linkedin.com/in/<user> 3. Click Add | Profile row appears (Processing → Ready); URL input hides while a profile exists |  | Not Started |  |  | Important
KB-002 | Knowledge Base | LinkedIn profile pulls real data | 1. Add a profile 2. Wait for Ready 3. Check summary / generate a post | Summary matches the real profile; no made-up or extra data |  | Not Started |  |  | Important
KB-003 | Knowledge Base | Reject non-profile URL | 1. In 'Your LinkedIn profile' enter a website or LinkedIn post URL | Toast: 'Enter a LinkedIn profile URL (linkedin.com/in/…)' |  | Not Started |  |  | Low
KB-004 | Knowledge Base | Delete LinkedIn profile | 1. Delete the profile row 2. Confirm | Row removed; profile URL input comes back |  | Not Started |  |  | Medium
KB-005 | Knowledge Base | Add website / link with note | 1. In Additional knowledge type a URL 2. Type a note (optional) 3. Click Add link | Row added with URL as title and 'Note: …' under it; goes Processing → Ready |  | Not Started |  |  | Important
KB-006 | Knowledge Base | URL validation | 1. Type 'hello', 'localhost', 'ftp://x', then 'acme.com' | Invalid ones: Add disabled + red 'Enter a valid link' after blur; acme.com is accepted |  | Not Started |  |  | Medium
KB-007 | Knowledge Base | Upload PDF with note | 1. Click Upload PDF 2. Pick a PDF, add a note 3. Click Upload | PDF row added with note; Processing → Ready |  | Not Started |  |  | Important
KB-008 | Knowledge Base | Cancel a staged PDF | 1. Pick a PDF 2. Click Cancel or ✕ | PDF is not uploaded; form is cleared |  | Not Started |  |  | Low
KB-009 | Knowledge Base | Edit / add a note on a source | 1. Click ✏️ on a note (or 'Add note for the agent') 2. Change text, press Enter | Note saved and shown; Esc cancels without saving |  | Not Started |  |  | Medium
KB-010 | Knowledge Base | Note max 200 characters | 1. Type a long note | Counter shows n/200; can't type past 200 |  | Not Started |  |  | Low
KB-011 | Knowledge Base | Delete a knowledge source | 1. Delete a website / PDF row 2. Confirm | Row removed; also gone from Composer settings → Knowledge |  | Not Started |  |  | Medium
KB-012 | Knowledge Base | Failed source shows error | 1. Add a broken / unreachable URL or bad PDF | Row shows Failed badge; app doesn't break |  | Not Started |  |  | Medium
KB-013 | Knowledge Base | Sources are clickable | 1. Click a website URL, profile URL, PDF name | Opens in a new tab |  | Not Started |  |  | Low
TONE-001 | Tone / Style | Add tone / style link | 1. In Tone / Style card type a blog or LinkedIn post URL + note 2. Add link | Row added, Processing → Ready, appears in Composer settings → Tone / Style |  | Not Started |  |  | Important
TONE-002 | Tone / Style | Add tone / style PDF | 1. Upload a PDF in Tone / Style with a note | Row added and processed |  | Not Started |  |  | Medium
TONE-003 | Tone / Style | Profile URL refused as tone source | 1. Enter linkedin.com/in/<user> in Tone / Style | Toast: LinkedIn profiles can't be a tone / style source |  | Not Started |  |  | Low
TONE-004 | Tone / Style | Generated post follows the voice | 1. Turn on one tone source 2. Generate posts | Post writing style clearly matches the sample |  | Not Started |  |  | Important
AUD-001 | Audience & Post Length | Target audience autosave | 1. Type a target audience 2. Stop typing / blur / close modal 3. Reload | 'Saving…' → 'Saved'; value is still there after reload |  | Not Started |  |  | Medium
AUD-002 | Audience & Post Length | Post length presets | 1. Click Short / Medium / Long / Let agent decide | Pill highlights and saves at once; survives reload |  | Not Started |  |  | Medium
AUD-003 | Audience & Post Length | Custom post length | 1. Type '150 words' in custom box | Saved; no pill highlighted; clearing it = Let agent decide |  | Not Started |  |  | Low
AUD-004 | Audience & Post Length | Audience & length used in posts | 1. Turn on 'Use target audience' and 'Use post length' in Composer settings 2. Generate | Posts target that audience and are about the chosen length |  | Not Started |  |  | Important
AUD-005 | Audience & Post Length | Toggles off = ignored | 1. Turn both toggles off 2. Generate | Audience / length values are not applied |  | Not Started |  |  | Medium
SET-001 | Composer Settings | Post count | 1. Set post count (e.g. 3) 2. Generate | Exactly that many drafts (1–20) |  | Not Started |  |  | Important
SET-002 | Composer Settings | Use hashtags on / off | 1. Toggle hashtags on, generate 2. Toggle off, generate | On: hashtags on last line (not repeated); Off: no hashtags |  | Not Started |  |  | Medium
SET-003 | Composer Settings | Use emoji on / off | 1. Toggle emoji on, generate 2. Toggle off, generate | Emoji only when on (or when the prompt / tone asks for it) |  | Not Started |  |  | Medium
SET-004 | Composer Settings | Use AI image off | 1. Turn off AI image 2. Generate | Drafts have no image and no image placeholder |  | Not Started |  |  | Medium
SET-005 | Composer Settings | Skip headline round | 1. Turn on ignore headline 2. Generate | No headline / concepts step; posts are written directly |  | Not Started |  |  | Medium
SET-006 | Composer Settings | Skip clarifying questions | 1. Turn on ignore questions 2. Generate | No question round (except attachment questions) |  | Not Started |  |  | Medium
SET-007 | Composer Settings | Knowledge switches | 1. Open Composer settings → Knowledge 2. Turn one source on, others off 3. Generate | Only the switched-on source is used; summary shows 'n of total on' |  | Not Started |  |  | Important
SET-008 | Composer Settings | All knowledge off | 1. Turn every knowledge source off 2. Generate | Posts written from the prompt only, no knowledge |  | Not Started |  |  | Medium
SET-009 | Composer Settings | Tone / style switches blend | 1. Turn on 2 tone sources 2. Generate 3. Turn all off, generate | 2 on = blended voice; all off = default voice |  | Not Started |  |  | Medium
SET-010 | Composer Settings | Empty knowledge list | 1. Use a workspace with no sources 2. Open Knowledge accordion | 'Nothing added yet — Add in Knowledge base' opens the modal |  | Not Started |  |  | Low
SET-011 | Composer Settings | Settings panel not cut off | 1. Expand Knowledge and Tone accordions with many sources | Panel stays fully visible and scrolls; list scrolls after 5 rows |  | Not Started |  |  | Low
SET-012 | Composer Settings | Settings saved after reload | 1. Change several toggles 2. Reload | All toggles keep their values |  | Not Started |  |  | Medium
SET-013 | Composer Settings | Writer AI model picker | 1. Click model pill 2. Switch provider tab, pick a model 3. Reload | Selected model is checked and stays after reload; used for next generation |  | Not Started |  |  | Medium
SET-014 | Composer Settings | Settings locked while running | 1. Start a generation 2. Try model picker / settings | Model picker disabled while running / waiting for answers |  | Not Started |  |  | Low
AGT-001 | Agent Chat (Generate Posts) | Generate posts from a prompt | 1. Open Automation 2. Type a prompt, Send 3. Answer any questions / approve headlines | Draft cards appear in the chat matching the prompt and settings |  | Not Started |  |  | Important
AGT-002 | Agent Chat (Generate Posts) | Clarifying questions form | 1. Send a prompt with questions on 2. Answer choice + free-text questions 3. Next / Submit | Defaults pre-selected; answers accepted; flow continues |  | Not Started |  |  | Important
AGT-003 | Agent Chat (Generate Posts) | Skip a question / skip questioning | 1. Switch a question off or click 'Skip questioning' | Agent continues without that answer |  | Not Started |  |  | Medium
AGT-004 | Agent Chat (Generate Posts) | Headlines / concepts round | 1. On the concepts card edit a line, delete one, add one 2. Generate drafts | One post per line in the approved list, first line matches |  | Not Started |  |  | Important
AGT-005 | Agent Chat (Generate Posts) | Suggest more concepts | 1. Click 'Suggest more concepts/ideas' | Card stays, shows 'Suggesting…' + skeleton rows, then new lines fade in |  | Not Started |  |  | Medium
AGT-006 | Agent Chat (Generate Posts) | Cancel a running generation | 1. Start a generation 2. Click Cancel | Run stops; chat can be used again |  | Not Started |  |  | Medium
AGT-007 | Agent Chat (Generate Posts) | Send blocked while running | 1. Start a generation 2. Try typing + Send | Send disabled until the run finishes |  | Not Started |  |  | Medium
AGT-008 | Agent Chat (Generate Posts) | New chat | 1. Click New chat | Empty chat; previous chat is in History |  | Not Started |  |  | Medium
AGT-009 | Agent Chat (Generate Posts) | History: open old conversation | 1. Open History 2. Click an old conversation | Whole conversation with its drafts loads |  | Not Started |  |  | Medium
AGT-010 | Agent Chat (Generate Posts) | Reload keeps the conversation | 1. Reload mid-conversation (also while running) | Same conversation re-opens; running state continues |  | Not Started |  |  | Medium
AGT-011 | Agent Chat (Generate Posts) | Clickable link in post body | 1. Prompt with a link (e.g. 'add link https://…') 2. Prompt without a link | With link: link is in the body and clickable; without: no link |  | Not Started |  |  | Medium
AGT-012 | Agent Chat (Generate Posts) | Very long prompt | 1. Paste a prompt over 4000 characters | Clear error, nothing breaks |  | Not Started |  |  | Low
AGT-013 | Agent Chat (Generate Posts) | Agent failure | 1. Cause a failed run (if possible) | Failure message in chat; user can send again |  | Not Started |  |  | Low
DRAFT-001 | Draft Cards (in chat) | Approve a draft | 1. Click ✓ on a draft card | Status changes to Approved; post appears in Post Management |  | Not Started |  |  | Important
DRAFT-002 | Draft Cards (in chat) | Approve with past publish time | 1. Approve a draft whose suggested time is in the past | Error toast + 'Edit Suggested Publish Time' modal opens pre-filled |  | Not Started |  |  | Medium
DRAFT-003 | Draft Cards (in chat) | Edit suggested publish time | 1. Click ✏️ next to the time 2. Pick a new date/time, Save | Time updated on the card |  | Not Started |  |  | Medium
DRAFT-004 | Draft Cards (in chat) | Past time is rejected inline | 1. Edit time to a past date, Save | Red error under the input, modal stays open, no toast |  | Not Started |  |  | Medium
DRAFT-005 | Draft Cards (in chat) | Edit text of a draft | 1. Hover a card → Edit text 2. Change text (bold, list), Save | Card shows new text; a 'You edited post N…' card appears in chat |  | Not Started |  |  | Important
DRAFT-006 | Draft Cards (in chat) | Edit image from a draft | 1. Hover a card → Edit image | Edit modal / image editor opens for that post |  | Not Started |  |  | Medium
DRAFT-007 | Draft Cards (in chat) | Edit a post by prompt | 1. After drafts: 'make post 2 longer', 'add emoji to post 1' | Only that post changes as asked, others untouched |  | Not Started |  |  | Important
DRAFT-008 | Draft Cards (in chat) | Edit by prompt following a link / tone | 1. Ask to update a post following a given link / tone sample | Post updated following that link / tone |  | Not Started |  |  | Medium
DRAFT-009 | Draft Cards (in chat) | Select a card to target the prompt | 1. Tick the checkbox on one card 2. Send a prompt | 'Prompting for: <headline>' pill shows; only that post is edited; selection clears after send |  | Not Started |  |  | Important
DRAFT-010 | Draft Cards (in chat) | Generate more drafts | 1. Click 'Generate more drafts' under a set | Skeleton cards append, then new drafts appear in the same set |  | Not Started |  |  | Medium
DRAFT-011 | Draft Cards (in chat) | Card actions on published post | 1. Find a published post card | No checkbox / edit for published posts |  | Not Started |  |  | Low
VER-001 | Post Version History | Old card shows old version | 1. Edit a post by prompt 2. Scroll up to the earlier card | Earlier card shows 'Old version · vN', no approve/edit |  | Not Started |  |  | Medium
VER-002 | Post Version History | Version history modal | 1. Click history icon on a card | All versions listed with source, date, prompt; Current tagged; Show full post works |  | Not Started |  |  | Medium
VER-003 | Post Version History | Use this version (restore) | 1. On an old card or in history click 'Use this version' | Old content comes back as a new version number; card becomes latest |  | Not Started |  |  | Important
VER-004 | Post Version History | Restore an approved post | 1. Approve a post 2. Restore an older version | Post goes back to Draft |  | Not Started |  |  | Medium
VER-005 | Post Version History | Read more on old version | 1. Click 'Read more' on an old card | Modal shows full old post with 'Use this version' |  | Not Started |  |  | Low
ATT-001 | Chat Attachments | Attach a PDF | 1. Click + → Upload a PDF 2. Pick file | 'Uploading…' chip → '#1 file.pdf' chip (blue when ready) |  | Not Started |  |  | Important
ATT-002 | Chat Attachments | Attach a URL | 1. Click + → Paste a URL → Add | '#n url' chip appears and turns ready |  | Not Started |  |  | Important
ATT-003 | Chat Attachments | Max 5 attachments | 1. Add 5 attachments 2. Open + again | 'Maximum 5 attachments reached.'; actions disabled |  | Not Started |  |  | Medium
ATT-004 | Chat Attachments | Numbers never reused | 1. Add #1, #2, #3 2. Remove #2 3. Add another | Chips: #1, #3, #4 |  | Not Started |  |  | Low
ATT-005 | Chat Attachments | Remove attachment | 1. Click × on a chip | Chip removed |  | Not Started |  |  | Medium
ATT-006 | Chat Attachments | Attachment used only when mentioned | 1. Attach a PDF 2. Send a prompt not mentioning it 3. Send 'use #1 as knowledge' | Step 2 ignores it; step 3 uses it |  | Not Started |  |  | Important
ATT-007 | Chat Attachments | Attachment as tone | 1. Send 'use #1 for tone' | Post follows the attachment's writing style |  | Not Started |  |  | Medium
ATT-008 | Chat Attachments | Unclear attachment question | 1. With 2 attachments send 'use the attachment' | Agent asks which one / how to use; Next disabled until picked |  | Not Started |  |  | Medium
ATT-009 | Chat Attachments | Failed attachment | 1. Attach a broken URL | Red 'Failed' chip with error on hover |  | Not Started |  |  | Low
ATT-010 | Chat Attachments | Send blocked while uploading | 1. Attach a big PDF and send right away | Can't send until upload is ready |  | Not Started |  |  | Low
RA-001 | Review & Approval | Drafts listed for review | 1. Open Post Management | All drafts show as cards with pagination |  | Not Started |  |  | Important
RA-002 | Review & Approval | Filter by conversation | 1. Pick a conversation in the filter | Only drafts from that conversation show |  | Not Started |  |  | Low
RA-003 | Review & Approval | Page size and pages | 1. Change page size (4–20) 2. Go to next page | Correct number of cards per page |  | Not Started |  |  | Low
RA-004 | Review & Approval | Approve from review | 1. Click ✓ on a review card | Post moves to Approved in the table |  | Not Started |  |  | Important
RA-005 | Review & Approval | Edit text from review | 1. Hover → Edit text 2. Change, Save | Post updated |  | Not Started |  |  | Medium
RA-006 | Review & Approval | Edit image from review | 1. Hover → Edit image | Opens Edit Image page for that post; back returns to review |  | Not Started |  |  | Medium
RA-007 | Review & Approval | Edit with agent | 1. Hover → Edit with agent 2. Send a change | Agent page opens with the post; the change is applied |  | Not Started |  |  | Important
RA-008 | Review & Approval | Edit with agent twice = same chat | 1. Click Edit with agent on the same post again | Opens the same conversation; no duplicate chat created |  | Not Started |  |  | Medium
PM-001 | Post Management | Stats cards | 1. Open Post Management 2. Compare numbers with real posts | Drafts / approved / scheduled / published / failed counts are correct |  | Not Started |  |  | Medium
PM-002 | Post Management | Filter by status | 1. Use Filter → each status | Only that status shows |  | Not Started |  |  | Medium
PM-003 | Post Management | Schedule an approved post | 1. Click Schedule on an approved post 2. Pick a future time | 'Post scheduled!' toast; status = Scheduled with that time |  | Not Started |  |  | Important
PM-004 | Post Management | Reschedule a scheduled post | 1. Click Reschedule 2. Pick new time | 'Post rescheduled!'; new time shown |  | Not Started |  |  | Important
PM-005 | Post Management | Re-schedule from the agent chat | 1. After a post is scheduled, ask the agent to change its time | Schedule updates correctly |  | Not Started |  |  | Medium
PM-006 | Post Management | Schedule in the past | 1. Try to schedule a past time | Rejected with clear error |  | Not Started |  |  | Medium
PM-007 | Post Management | Move back to draft | 1. Click Move back to draft on approved / scheduled post 2. Confirm | Post is Draft again and in Review |  | Not Started |  |  | Medium
PM-008 | Post Management | Delete a post | 1. Delete a post 2. Confirm | 'Post deleted.'; removed everywhere |  | Not Started |  |  | Medium
PM-009 | Post Management | Bulk delete | 1. Select several posts 2. Delete | 'N posts deleted.' |  | Not Started |  |  | Low
PM-010 | Post Management | Calendar view drag to reschedule | 1. Switch to calendar (month / week) 2. Drag a post to another day | 'Post moved.' and date updated |  | Not Started |  |  | Low
PM-011 | Post Management | Open published post on LinkedIn | 1. Click LinkedIn link on a published post | Opens the real post on LinkedIn |  | Not Started |  |  | Low
PUB-001 | Publishing | Scheduled post publishes on time | 1. Schedule a post a few minutes ahead 2. Wait | Post is live on LinkedIn at that time; status = Published |  | Not Started |  |  | Important
PUB-002 | Publishing | Published post content is correct | 1. Compare the LinkedIn post with the draft | Text, line breaks, emoji, hashtags, link and image match |  | Not Started |  |  | Important
PUB-003 | Publishing | Publish fails gracefully | 1. Disconnect LinkedIn / expire token 2. Let a scheduled post run | Status = Failed with a reason; no silent loss |  | Not Started |  |  | Medium
IMG-001 | Edit Image (Image Chat) | Open Edit Image page | 1. Open Edit image on a post | Chat, post preview and media tabs load; existing image shown |  | Not Started |  |  | Important
IMG-002 | Edit Image (Image Chat) | Generate an image from prompt | 1. Type a prompt, Send | Your message shows at once; thinking steps; image appears |  | Not Started |  |  | Important
IMG-003 | Edit Image (Image Chat) | Add image to post | 1. Click Add to post on an image | Preview + media update; button shows Added |  | Not Started |  |  | Important
IMG-004 | Edit Image (Image Chat) | Added state survives reload | 1. Reload after adding | Preview, media and Added button still correct |  | Not Started |  |  | Medium
IMG-005 | Edit Image (Image Chat) | Delete post image | 1. Delete image in media section | Image removed from post |  | Not Started |  |  | Medium
IMG-006 | Edit Image (Image Chat) | Edit an existing image by prompt | 1. Ask 'make it realistic' / 'change background to blue' | New image follows the request |  | Not Started |  |  | Important
IMG-007 | Edit Image (Image Chat) | 'AI generated image' suggestion | 1. Click 'AI generated image' link under the last message | A new AI image is generated |  | Not Started |  |  | Medium
IMG-008 | Edit Image (Image Chat) | Use post body on / off | 1. Toggle Use post body in Image agent settings 2. Generate | On: image relates to the post; Off: follows prompt only |  | Not Started |  |  | Medium
IMG-009 | Edit Image (Image Chat) | Change AI model | 1. Open AI model menu, pick another | Selection saved; next image uses it |  | Not Started |  |  | Medium
IMG-010 | Edit Image (Image Chat) | Change image style | 1. Open Style menu, pick a style (or None) | Next image uses that style |  | Not Started |  |  | Medium
IMG-011 | Edit Image (Image Chat) | Change media size / ratio | 1. Open ratio, pick e.g. 1:1 or 16:9 | Next image is in that ratio |  | Not Started |  |  | Medium
IMG-012 | Edit Image (Image Chat) | Image sizes look right | 1. Generate landscape, portrait, square | No cropping in chat, preview, lightbox |  | Not Started |  |  | Low
IMG-013 | Edit Image (Image Chat) | Download / open large image | 1. Click image → lightbox 2. Download | Large view opens; file downloads |  | Not Started |  |  | Low
IMG-014 | Edit Image (Image Chat) | Chat scroll | 1. Open a long chat 2. Scroll up, then use 'Scroll to newest' | Opens at bottom; scroll button jumps to newest |  | Not Started |  |  | Low
IMG-015 | Edit Image (Image Chat) | Published post is read-only | 1. Open Edit image for a published post | No composer / stock button |  | Not Started |  |  | Low
IMG-016 | Edit Image (Image Chat) | Disabled toolbar buttons | 1. Hover emoji / paperclip | Disabled with 'Soon' tooltip |  | Not Started |  |  | Low
STOCK-001 | Stock Image (Pexels) | Recommended stock photos | 1. Click Stock image | Photos recommended for the post load (skeleton first) |  | Not Started |  |  | Medium
STOCK-002 | Stock Image (Pexels) | Search stock photos | 1. Type a search 2. Scroll down | Results update as you type; more load on scroll |  | Not Started |  |  | Medium
STOCK-003 | Stock Image (Pexels) | Add stock photo to post | 1. Hover a photo → Add to post | Modal closes; post image updated; 'Added a stock photo' card in chat |  | Not Started |  |  | Important
STOCK-004 | Stock Image (Pexels) | Large preview | 1. Click a photo | Large view with photographer + Back / Add to post |  | Not Started |  |  | Low
STOCK-005 | Stock Image (Pexels) | Modal closes only with ✕ | 1. Click outside / press Esc | Modal stays open |  | Not Started |  |  | Low
STOCK-006 | Stock Image (Pexels) | No results / error | 1. Search nonsense text | 'No photos found for …'; errors show Retry |  | Not Started |  |  | Low
IKB-001 | Image Knowledge Base | Add image knowledge link / PDF | 1. Open Image knowledge base 2. Add URL or PDF with note | Source added, Pending → Ready, switched On |  | Not Started |  |  | Medium
IKB-002 | Image Knowledge Base | Write it yourself (text) | 1. Type brand rules in the text box 2. Add text | Text source added (max 8,000 chars) |  | Not Started |  |  | Medium
IKB-003 | Image Knowledge Base | Edit a text source | 1. Click pencil on a text row 2. Change, Save changes | Text updated, same position and switch |  | Not Started |  |  | Low
IKB-004 | Image Knowledge Base | Delete image knowledge source | 1. Delete a row, confirm | Removed from list and settings |  | Not Started |  |  | Low
IKB-005 | Image Knowledge Base | Image knowledge switches | 1. In Image agent settings turn sources on / off | Each switch independent; saved |  | Not Started |  |  | Medium
IKB-006 | Image Knowledge Base | Images follow image knowledge | 1. Add brand rules (e.g. colors) 2. Turn on 3. Generate image | Image follows the brand guide |  | Not Started |  |  | Important
Medium
Low
Medium
Low
Low

## Summary
Test Summary (updates automatically from 'Test Cases')
Overall | Count
Total test cases | 145
Not Started | 143
In Progress | 0
Pass | 2
Fail | 0
Blocked | 0
Not Applicable | 0
Pass rate (of tested) | 100%
Priority | Total | Pass | Fail | In Progress | Not Started | Blocked
Important | 41 | 1 | 0 | 0 | 40 | 0
Medium | 70 | 1 | 0 | 0 | 67 | 0
Low | 39 | 0 | 0 | 0 | 36 | 0
Feature Area | Total | Pass | Fail | In Progress | Not Started | Blocked | Important
Login & Account | 8 | 2 | 0 | 0 | 6 | 0 | 4
Workspace | 4 | 0 | 0 | 0 | 4 | 0 | 2
Navigation & Layout | 4 | 0 | 0 | 0 | 4 | 0 | 0
LinkedIn Account Connection | 4 | 0 | 0 | 0 | 4 | 0 | 2
Knowledge Base | 13 | 0 | 0 | 0 | 13 | 0 | 4
Tone / Style | 4 | 0 | 0 | 0 | 4 | 0 | 2
Audience & Post Length | 5 | 0 | 0 | 0 | 5 | 0 | 1
Composer Settings | 14 | 0 | 0 | 0 | 14 | 0 | 2
Agent Chat (Generate Posts) | 13 | 0 | 0 | 0 | 13 | 0 | 3
Draft Cards (in chat) | 11 | 0 | 0 | 0 | 11 | 0 | 4
Post Version History | 5 | 0 | 0 | 0 | 5 | 0 | 1
Chat Attachments | 10 | 0 | 0 | 0 | 10 | 0 | 3
Review & Approval | 8 | 0 | 0 | 0 | 8 | 0 | 3
Post Management | 11 | 0 | 0 | 0 | 11 | 0 | 2
Publishing | 3 | 0 | 0 | 0 | 3 | 0 | 2
Edit Image (Image Chat) | 16 | 0 | 0 | 0 | 16 | 0 | 4
Stock Image (Pexels) | 6 | 0 | 0 | 0 | 6 | 0 | 1
Image Knowledge Base | 6 | 0 | 0 | 0 | 6 | 0 | 1
Leads | 0 | 0 | 0 | 0 | 0 | 0 | 0

## How to use
How to use this sheet
Columns A–I | Same order as the existing tester sheet (Test ID → Comments), so rows can be copied between both sheets. Priority is the extra column J.
Fill in | Tester fills only: Actual Result (F), Status (G), Tester (H), Comments (I). Columns A–E and J are the test plan.
Status | Not Started · In Progress · Pass · Fail · Blocked (can't test, e.g. backend down) · Not Applicable. A Fail turns the row pink.
Priority | Important = core flow; a fail blocks release (login, generate, approve, schedule, publish, data isolation). Medium = main feature works but a secondary path is broken. Low = cosmetic, edge case, or nice-to-have.
New cases | 30 empty rows are left under the last case. Use the same prefix + next number (e.g. IMG-017).
Summary tab | Counts by status, priority and feature area — updates on its own.
Example | Actual Result: 'Image stays the same, only colours change' · Status: Fail · Tester: Sazzad · Comments: 'Prompt: make it realistic — link / screenshot'
ID prefixes | LOGIN = Login & Account, WS = Workspace, NAV = Navigation & Layout, ACC = LinkedIn Account Connection, KB = Knowledge Base, TONE = Tone / Style, AUD = Audience & Post Length, SET = Composer Settings, AGT = Agent Chat (Generate Posts), DRAFT = Draft Cards (in chat), VER = Post Version History, ATT = Chat Attachments, RA = Review & Approval, PM = Post Management, PUB = Publishing, IMG = Edit Image (Image Chat), STOCK = Stock Image (Pexels), IKB = Image Knowledge Base, LEADS = Leads